## Multi-Season SU17-SU20
Category GamePlan: Multi-Season Calendar
| 2016 | [52 empty] | 2017 | [21 empty] | CGP MASTER CALENDAR DATE RANGE | [29 empty] | 2018 | [51 empty] | 2019 | [51 empty] | 2020
| 2016-12-28 | 2017-01-04 | 2017-01-11 | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-08 | 2017-02-15 | 2017-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18 | 2016-07-25 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29 | 2016-09-05 | 2016-09-12 | 2016-09-19 | 2016-09-26 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28
| Nike Holiday | [5 empty] | Chinese New Year 2/8 | [5 empty] | WHQ SB | [38 empty] | Nike Holiday | Nike Holiday |  |  |  | Chinese NY | [8 empty] | WHQ SB | [38 empty] | Nike Holiday | Nike Holiday | [5 empty] | Chinese NY | [5 empty] | WHQ SB (TBC) | [38 empty] | Nike Holiday | Nike Holiday |  |  |  |  | Chinese New Year 2/5 | [6 empty] | WHQ SB (TBC) | [38 empty] | Nike Holiday | Nike Holiday |  |  | Chinese New Year 1/25 | [9 empty] | WHQ SB (TBC) | [37 empty] | Nike Holiday | Nike Holiday
| 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
SU17 | [7 empty] | Category Alignment | [10 empty] | Assort. Finalization | [7 empty] | Seasonal Integrat. | [6 empty] | Go-to-Market | [6 empty] | 1st Futures Order Deadline - 10/7
| 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
FA17 |  |  |  |  | Design Review | [15 empty] | Category Alignment | [10 empty] | Assort. Finalization | [7 empty] | Seasonal Integrat. | [6 empty] | Go-to-Market | [6 empty] | 1st Futures Order Deadline - 1/6
| 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
HO17 | [17 empty] | Design Review (4/25-26) |  | Concept Review (5/13) | [13 empty] | Category Alignment | [10 empty] | Assort. Finalization | [10 empty] | Seasonal Integration |  |  |  | Go-to-Market | [6 empty] | 1st Futures Order Deadline - 4/7
[13 empty] | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
SP18 | [6 empty] | SP18 | [19 empty] | Design Review |  | Concept Review (7/13) | [12 empty] | Category Alignment | [17 empty] | Assort. Finalization | [5 empty] | Seasonal Integration |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 7/7
[13 empty] | 104 |  | 102 | 101 | 100 |  | 98 | 97 | 96 | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
SU18 | [6 empty] | SU18 | [32 empty] | Design Review |  |  | Concept Review (10/18) | [11 empty] | Category Alignment | [17 empty] | Assort. Finalization | [5 empty] | Seasonal Integration |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 10/6
[35 empty] | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
FA18 | [28 empty] | FA18 | [21 empty] | Design Review | [5 empty] | Concept Review (1/24) | [10 empty] | Category Alignment | [17 empty] | Assort. Finalization | [5 empty] | Seasonal Integration |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 1/5
[35 empty] | 108 | 107 |  | 105 | 104 | 103 | 102 | 101 |  | 99 | 98 | 97 | 96 | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
HO18 | [28 empty] | HO18 | [35 empty] | Design Review (3/21-23) |  |  |  | Concept Review (4/21) | [11 empty] | Category Alignment (7/12-18) | [17 empty] | Assort. Finalization |  |  |  |  | Seasonal Integrat. |  |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 4/6
[61 empty] | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
SP19 | [54 empty] | SP19 | [23 empty] | Design Review (6/26-27) | [14 empty] | Category Alignment | [17 empty] | Assort. Finalization |  |  |  |  | Seasonal Integrat. |  |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 7/6
[61 empty] | 108 | 107 | 106 |  | 104 | 103 |  | 101 | 100 | 99 | 98 | 97 | 96 | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
SU19 | [54 empty] | SU19 | [36 empty] | Design Review (TBC) | [14 empty] | Category Alignment | [17 empty] | Assort. Finalization | [5 empty] | Seasonal Integrat. |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 10/5
[87 empty] | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
FA19 | [80 empty] | FA19 | [21 empty] | Design Review (TBC) | [16 empty] | Category Alignment | [17 empty] | Assort. Finalization | [6 empty] | Seasonal Integrat. |  |  | KAPM | [10 empty] | 1st Futures Order Deadline - 1/11
[87 empty] | 108 | 107 | 106 |  | 104 | 103 | 102 | 101 |  | 99 | 98 | 97 | 96 | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13
HO19 | [80 empty] | HO19 | [35 empty] | Design Review (TBC) | [15 empty] | Category Alignment | [17 empty] | Assort. Finalization | [5 empty] | Seasonal Integrat. |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 4/5
[113 empty] | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | X
SP20 | [106 empty] | SP20 | [23 empty] | Design Review (TBC) | [14 empty] | Category Alignment | [17 empty] | Assort. Finalization | [5 empty] | Seasonal Integrat. |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 7/5
[114 empty] | 107 | 106 | 105 | 104 | 103 |  | 101 | 100 | 99 | 98 | 97 | 96 | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | X
SU20 | [106 empty] | SU20 | [36 empty] | Design Review | [14 empty] | Category Alignment | [17 empty] | Assort. Finalization | [5 empty] | Seasonal Integrat. |  |  |  | KAPM | [9 empty] | 1st Futures Order Deadline - 10/4
[139 empty] | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | X
FA20 | [132 empty] | FA20 | [21 empty] | Design Review | [16 empty] | Category Alignment | [17 empty] | Assort. Finalization | [6 empty] | Seasonal Integrat. |  |  | KAPM | [10 empty] | 1st Futures Order Deadline - 1/10
[139 empty] | 108 | 107 |  | 105 | 104 |  | 102 | 101 | 100 | 99 | 98 | 97 | 96 | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | X | X
HO20 | [132 empty] | HO20 | [35 empty] | Design Review | [15 empty] | Category Alignment | [17 empty] | Assort. Finalization | [5 empty] | Seasonal Integrat. | [5 empty] | Go-to-Market (TBC) | [7 empty] | 1st Futures Order Deadline - 4/3
Today
1st Opportunity for FA08 Alignment
Today
CATEGORY GAME PLAN MULTI-SEASON CALENDAR
Concept Launch (4/25)
Concept Launch (10/18)
Concept Launch (4/7)
Concept Review
Innovation Launch &
Creative Launch
Concept Launch (10/18)
Innovation Launch & Creative Launch (3/15)
Innovation Launch & Creative Launch (9/14)
Innovation Launch & Creative Launch (3/31)
Innovation & Creative Launch (9/7)
Concept Launch (TBC)
Concept Review
Innovation Launch &
Creative Launch
Concept Launch (TBC)
Innovation Launch & Creative Launch (TBC)
Innovation Launch & Creative Launch (TBC)
IN RETAIL
IN RETAIL
IN RETAIL
IN RETAIL
IN RETAIL
IN RETAIL
IN RETAIL
IN RETAIL
IN RETAIL
IN RETAIL
IN RETAIL

## Change Tracker (hidden)
Date | Change made
2009-01-07 | Moved SP10 GTM meeting date to 5/25/09
Moved SU10 GTM meeting date to 8/24
2009-01-12 | Added Futures Order Deadlines dates
2009-02-18 | Updated HO10 and added SP11, SU11, FA11, HO11
Updated date of FA10 IGTM from 8/6 to 9/2
Created new multi-season calendar with all three seasons
Added Global holidays from last tab
2008-04-13 | Added SP11 - 15.5 month calendar
Removed 2009 calendar
Only one calendar page
Changed colors of the IDCR & RLF milestones to reflect subway chart

## Global Holidays (hidden)
| 2008 | 2009 | 2010 | 2011 | 2012
Lunar New Year | 2008-02-04 | 2009-01-26 | 2010-02-15 | 2011-01-31 | 2012-01-23
Spring Break | 2008-03-24 | 2009-03-23 | 2010-03-22 | TBD | TBD
Thanksgiving | 2008-11-24 | 2009-11-23 | 2010-11-22 | 2011-11-21 | 2012-11-19
Christmas | 2008-12-22 | 2009-12-21 | 2010-12-20 | 2011-12-19 | 2012-12-24
New Years | 2008-12-29 | 2009-12-28 | 2010-12-27 | 2011-12-26 | 2012-12-31

## Logic + Rules
How to Establish Calendar Week #s
Date
2016-05-19 | 1) Protect 13 week gap between seasons – copy and paste previous season's weeks to maintain 13 week difference 2) Establish First Futures Order deadline at first Friday 6-months prior to season's first offer – SP (July), SU (October), FA (January), HO (April). Record date – will be on Week 24 or 23 3) Use "x"'s in week cells to align weeks to season's first offer – SP (January), SU (April), FA (July), HO (October) 4) Plot gates according to CGP timeline and make adjustments according to "Logic + Rules"
2017-01-26 | First Offer date to retailers has to do with Logistics and Operations time lines in order to set Retail Floors on the first day of the new Season. Example: SP 17 – Dec 26th ’16 (Monday), SU 17 – Mar 27th ‘17 (Monday), FA 17 – June 26th ’17 (Monday), HO 17 – Sept 25th ’17 (Monday)
2017-01-26 | First In-Season week in Retail from Merchandising: Assortments for new season will land first week of Jan, April, July, October.
Change Log |  |  |  |  | Logic + Rules | [5 empty] | First Futures Order Deadline Date
Date | Change | Gate Impacted | Effective Season | Reason | Date | Topic | Seasons Impacted | Gate Impacted | Rule/Logic | Reason | First Futures Order Deadline Date should be the first Friday of the month 6-months prior to First Offer – SP (Jul), SU (Oct), FA (Jan), HO (Apr) *Exception: FA seasons – First Futures Order Deadline is the Friday in the first FULL week of January.
2016-05-03 | HO17 CR added to season on 4/13/16 | CR | HO17 | Best practice pulled forward from SPSU18 to align on lead Concepts for Future Court | 2016-05-19 | Spring Break | HO | DR | If Spring Break falls on DR week (HO-only), pull DR to week before holiday | Design prefers to hold DR BEFORE Spring Break | Season | Year | First Offer (static) | First Futures (variable – First Friday, 6 mo. prior to First Offer) | Confirmed
2016-05-03 | FAHO18 CL moved from week 95 (with IL) to week 93 | CL | FAHO18 | Leadership unavailble during week 95 | 2016-05-19 | Winter Break | FA/HO | IL-DR | Due to winter Holiday, IL-DR is pulled back two weeks – IL should fall on week 95 | Design prefers to hold DR BEFORE Holiday Break | FA | 2016 | 2016-07-01 | 2016-01-08 | 2014-01-01
2016-05-03 | FA19 CR moved from week 75 to 74 | CR | FA19 | Moved to accommodate WHQ holiday (not week immediately following break) and after SP19 PRO week | 2016-05-19 | Concept Launch/DR Overlap | SU/HO | DR | Trailing season DR may be shortened to include the following season's Concept Lanch | Trailing seasons are historically lighter on presenting categories and relevant seasonal products – given the seasonal overlap conflict, it's acceptable to align the two gates on the same week | HO |  | 2016-10-01 | 2016-04-08 | 2014-01-01
2016-07-07 | FA19 DR moved to week 79 | DR | FA19 | Moved to accommodate WHQ holiday (not week immediately before break) | 2016-05-19 | Assort Final/GTM Overlap | All Seasons | GTM | AF must be on week 44 so previous seasons' GTM can move from Week 31 to Week 32 | GTM within a Geo is fluid – the exact date of 31 is not necessary | SP | 2017 | 2017-01-01 | 2016-07-08 | 2014-01-01
[5 empty] | 2016-05-19 | First Futures Order Deadline | FA | All Gates | If first Friday in January isn't first full week of January, move to second week | Weeks need full week prior to holiday to place orders. Partial weeks are interupted by the winter holiday | SU |  | 2017-04-01 | 2016-10-07 | 2014-01-01
[11 empty] | FA |  | 2017-07-01 | 2017-01-06 | 2014-01-01
[11 empty] | HO |  | 2017-10-01 | 2017-04-07 | 2014-01-01
[11 empty] | SP | 2018 | 2018-01-01 | 2017-07-07 | 2014-01-01
[11 empty] | SU |  | 2018-04-01 | 2017-10-06 | 2014-01-01
[11 empty] | FA |  | 2018-07-01 | 2018-01-05 | 2014-01-01
[11 empty] | HO |  | 2018-10-01 | 2018-04-06 | 2014-01-01
[11 empty] | SP | 2019 | 2019-01-01 | 2018-07-06 | 2016-05-25
[11 empty] | SU |  | 2019-04-01 | 2018-10-05 | 2016-05-25
[11 empty] | FA |  | 2019-07-01 | 1/11/19* | 2016-05-25
[11 empty] | HO |  | 2019-10-01 | 2019-04-05 | 2016-05-25
[11 empty] | SP | 2020 | 2020-01-01 | 2019-07-05 | 2016-05-25
[11 empty] | SU |  | 2020-04-01 | 2019-10-04 | 2016-05-25
[11 empty] | FA |  | 2020-07-01 | 1/10/20* | 2016-05-25
[11 empty] | HO |  | 2020-10-01 | 2020-04-03 | 2016-05-25
[11 empty] | SP | 2021 | 2021-01-01 | 2020-07-03
[11 empty] | SU |  | 2021-04-01 | 2020-10-02
[11 empty] | FA |  | 2021-07-01 | 1/8/21*
[11 empty] | HO |  | 2021-10-01 | 2021-04-02
[11 empty] | SP | 2022 | 2022-01-01 | 2021-07-02
[11 empty] | SU |  | 2022-04-01 | 2021-10-01
[11 empty] | FA |  | 2022-07-01 | 1/7/22*
[11 empty] | HO |  | 2022-10-01 | 2022-04-01